## Sheet1
Communication and Dissemination Plan for the Helsinki Declaration on Patient Safety at Home. To maximise the visibility, uptake, and dissemination of the Helsinki Declaration across BetterCare member countries and relevant European and international networks, engaging both professional and public stakeholders. | Timeline - Deadline | Activity to be done BY WHOM? | Alternative Person for Activity | Activity done by Whom? | Done | Pending
Communication materials, what BETTERCARE needs to upload on the website:
| By 8th September 2026 | Alejandro Rodriguez Sanchez <alejandro.rodriguezs@umh.es>
• Helsinki Declaration full text, already included | By 8th September 2026 | Alejandro Rodriguez Sanchez <alejandro.rodriguezs@umh.es>
• Short explanatory text summarising its purpose and key messages, already worked by Sandra BUTTIGIEG | By 8th September 2026 | Alejandro Rodriguez Sanchez <alejandro.rodriguezs@umh.es>
• Dedicated iconography and visual materials, already ready but not upload on the website | By 8th September 2026 | Alejandro Rodriguez Sanchez <alejandro.rodriguezs@umh.es>
• Promotional video, expected in September. | By 8th September 2026 | Alejandro Rodriguez Sanchez <alejandro.rodriguezs@umh.es>
Internal mobilisation within BetterCare
The standard messages Sandra BUTTIGIEG has already prepared for - view ATTACHMENTS | By 12 th September 2026 | Nazaret Fernandez Muñoz <nazaret.fernandez@umh.es>/Hana Knežević <hana.knezevic91@gmail.com> and the COST Communication Team
• Core Group members. | By 12 th September 2027 | Nazaret Fernandez Muñoz <nazaret.fernandez@umh.es>/Hana Knežević <hana.knezevic91@gmail.com> and the COST Communication Team
• Management Committee members. | By 12 th September 2028 | Nazaret Fernandez Muñoz <nazaret.fernandez@umh.es>/Hana Knežević <hana.knezevic91@gmail.com> and the COST Communication Team
• All BetterCare participants and also diverse publics who participated in diverse activities (Alejandro has the list) such as Forum, Webinars, and so on - so-called “Friends of BetterCare” | By 12 th September 2029 | Nazaret Fernandez Muñoz <nazaret.fernandez@umh.es>
Once the promotional video is available in September, these messages should be circulated asking MC members to: | By 20th September 2026 | MC MEMBERS to report to Nazaret Fernandez Muñoz <nazaret.fernandez@umh.es>/Hana Knežević <hana.knezevic91@gmail.com> and COST Communication Team
• Disseminate the Declaration through their institutional and professional networks. | By 20th September 2028 | MC MEMBERS to report to Nazaret Fernandez Muñoz <nazaret.fernandez@umh.es>/Hana Knežević <hana.knezevic91@gmail.com> and COST Communication Team
• Share the communication materials nationally. | By 20th September 2029 | MC MEMBERS to report to Nazaret Fernandez Muñoz <nazaret.fernandez@umh.es>/Hana Knežević <hana.knezevic91@gmail.com> and COST Communication Team
• Identify relevant organisations, stakeholders, and dissemination opportunities within their countries. | By 20th September 2030 | MC MEMBERS to report to Nazaret Fernandez Muñoz <nazaret.fernandez@umh.es>/Hana Knežević <hana.knezevic91@gmail.com> and COST Communication Team
In parallel, Friends of BetterCare could receive the video and a shot message with the link of the Helsinki Declaration | By the 20th September 2026 | Nazaret Fernandez Muñoz <nazaret.fernandez@umh.es>/Hana Knežević <hana.knezevic91@gmail.com> and the COST Communication Team
External institutional dissemination
Targeted messages should be prepared for major European and international stakeholders, including:
• WHO and other international health organisations.
• European institutions and relevant EU agencies.
• European Parliament health-related groups and committees.
• National Ministries of Health and Social Affairs.
• National health and social care agencies.
• Scientific and professional societies.
• Networks of Informal caregiver organisations and networks, including Eurocarers.
• Other organisations working in long-term care, home care, ageing, patient safety, and integrated care.
These communications should be launched once the promotional video is available, providing direct access to the Declaration and supporting materials and encouraging further dissemination through their networks.
European media strategy |  | Hana Knežević <hana.knezevic91@gmail.com> and the COST Communication Team
A European-level press release should be prepared and disseminated directly to relevant media contacts through Hana and the COST communication team. | 30th September 2026 | Hana Knežević <hana.knezevic91@gmail.com> and the COST Communication Team
National media dissemination | 25th September 2026 | MC MEMBERS to report to Nazaret Fernandez Muñoz <nazaret.fernandez@umh.es>
A standard press release template should be prepared centrally (we prepared a text for Spain). | 26th September 2026 | Translation from Spanish to English by Central office ??
By last-September, Management Committee members should be invited in a second mail to: | 27th September 2026 | MC MEMBERS to report to Nazaret Fernandez Muñoz <nazaret.fernandez@umh.es>/Hana Knežević <hana.knezevic91@gmail.com> and COST Communication Team
| 28th September 2026 | MC MEMBERS to report to Nazaret Fernandez Muñoz <nazaret.fernandez@umh.es>/Hana Knežević <hana.knezevic91@gmail.com> and COST Communication Team
• Adapt the press release to their national context. | 29th September 2026 | MC MEMBERS to report to Nazaret Fernandez Muñoz <nazaret.fernandez@umh.es>/Hana Knežević <hana.knezevic91@gmail.com> and COST Communication Team
• Send it to relevant national and regional media. | 30th September 2026 | MC MEMBERS to report to Nazaret Fernandez Muñoz <nazaret.fernandez@umh.es>/Hana Knežević <hana.knezevic91@gmail.com> and COST Communication Team
• Inform Hana or you of the media outlets contacted. | 31st September 2026 | MC MEMBERS to report to Nazaret Fernandez Muñoz <nazaret.fernandez@umh.es>/Hana Knežević <hana.knezevic91@gmail.com> and COST Communication Team